## Data Analyst Project Scedule
Date | Day | Task(s) Assigned to Students | Key Deliverable
2025
2025-10-15 | Wednesday | NDA document signing and review, Kick-off meeting | Signed NDA, Project kickoff
2025-10-16 | Thursday | Develop Project Charter, Create Data Dictionary | Project Charter Document, Data Dictionary (Initial Draft)
2025-10-17 | Friday | (Buffer Day / Review Oct 15-16 tasks) | (Review/Refine Deliverables)
2025-10-20 | Monday | Begin work on Architecture Diagram
2025-10-21 | Tuesday | Complete Architecture Diagram | Architecture Diagram
2025-10-22 | Wednesday | Data Preprocessing (Cleaning, transformation, etc.) | Cleaned Dataset, Preprocessing Script
2025-10-23 | Thursday | Continue Data Preprocessing / Begin EDA setup
2025-10-24 | Friday | Data Visualization and Exploratory Data Analysis (EDA) | EDA Report/Notebook, Initial Visualizations
2025-10-27 | Monday | Develop and test SQL Queries | Documented SQL Queries
2025-10-28 | Tuesday | (Buffer Day / Review Oct 24 & 27 tasks) | (Review/Refine EDA & SQL)
2025-10-29 | Wednesday | Begin Power BI Visualization dashboard creation | Power BI (or other BI tool) file setup
2025-10-30 | Thursday | Continue Power BI Visualization development | Power BI Dashboard (WIP)
2025-10-31 | Friday | Finalize Power BI Visualization dashboard | Final Power BI Dashboard
2025-11-01 | Saturday | (Self-Study / Final Project Review) | (Prepare presentation/summary)
2025-11-02 | Sunday | Mock Interview Preparation (Reviewing project, preparing behavioral and technical answers) | Mock Interview Readiness